## Task_Table1
ID | Indicators | Task_Name | Duration | Start_Date | Finish_Date | Predecessors | Resource_Names
0 |  |  | 42.5 days? | 2017-01-02 08:00 | 2017-02-27 12:00
1 |  | Perform Initial Planning | 6 days? | 2017-01-03 08:00 | 2017-01-10 17:00
2 |  | Review project file/lessons learned from last year's Annual Report process | 1 day? | 2017-01-03 08:00 | 2017-01-03 17:00 |  | Strategic Planning Committee
3 |  | Confirm changes, if any, to financial reporting requirements | 1 day? | 2017-01-04 08:00 | 2017-01-04 17:00 | 2 | CFO/Controller
4 |  | Identify Annual Report Theme and Section Requirements | 1 day? | 2017-01-05 08:00 | 2017-01-05 17:00 | 3 | Strategic Planning Committee
5 |  | Confirm other sections to be added or removed | 1 day? | 2017-01-06 08:00 | 2017-01-06 17:00 | 4 | Strategic Planning Committee
6 |  | Confirm SEC filing and Annual Report Checkpoints | 1 day? | 2017-01-09 08:00 | 2017-01-09 17:00 | 5 | CFO/Controller
7 |  | Selection of Internal Auditors | 1 day? | 2017-01-10 08:00 | 2017-01-10 17:00 | 6 | Audit Committee
8 |  | Initial Planning Complete | 0 days | 2017-01-10 17:00 | 2017-01-10 17:00 | 7
9 |  | Design Annual Report | 6 days? | 2017-01-11 08:00 | 2017-01-18 17:00
10 |  | Assign resources to preliminary design | 1 day? | 2017-01-11 08:00 | 2017-01-11 17:00 | 8 | Strategic Planning Committee
11 |  | Develop preliminary design and information requirements | 1 day? | 2017-01-12 08:00 | 2017-01-12 17:00 | 10 | Strategic Planning Committee
12 |  | Evaluate/Confirm Report Distribution Mechanisms | 3 days? | 2017-01-13 08:00 | 2017-01-17 17:00
13 |  | Evaluate/confirm Annual Report design and communications vendor(s) | 1 day? | 2017-01-13 08:00 | 2017-01-13 17:00 | 11 | PR/IR Dept
14 |  | Evaluate/confirm corporate Web site design and integration requirements | 1 day? | 2017-01-16 08:00 | 2017-01-16 17:00 | 13 | PR/IR Dept
15 |  | Evaluate/confirm Annual Report production and mailing vendor(s) | 1 day? | 2017-01-17 08:00 | 2017-01-17 17:00 | 14 | PR/IR Dept
16 |  | Report Distribution Mechanisms Confirmed | 0 days | 2017-01-17 17:00 | 2017-01-17 17:00 | 15 | PR/IR Dept
17 |  | Plan/confirm production schedule | 1 day? | 2017-01-18 08:00 | 2017-01-18 17:00 | 16 | PR/IR Dept
18 |  | Annual Report Design Complete | 0 days | 2017-01-18 17:00 | 2017-01-18 17:00 | 17
19 |  | Define SEC 10-K and Proxy Documentation Production Schedules | 3 days? | 2017-01-19 08:00 | 2017-01-23 17:00
20 |  | Plan/confirm 10-K production schedule | 1 day? | 2017-01-19 08:00 | 2017-01-19 17:00 | 18 | CFO/Controller
21 |  | Plan/confirm Proxy Statement production schedule | 1 day? | 2017-01-20 08:00 | 2017-01-20 17:00 | 20 | CFO/Controller
22 |  | Identify process steps required to meet production schedule | 1 day? | 2017-01-23 08:00 | 2017-01-23 17:00 | 21 | CFO/Controller
23 |  | SEC 10-K and Proxy Documentation Production Schedules Complete | 0 days | 2017-01-23 17:00 | 2017-01-23 17:00 | 22
24 |  | Develop Annual Report | 22 days? | 2017-01-24 08:00 | 2017-02-22 17:00
25 |  | Develop Theme production components | 7 days? | 2017-01-24 08:00 | 2017-02-01 17:00
26 |  | Schedule and hold Theme development sessions | 1 day? | 2017-01-24 08:00 | 2017-01-24 17:00 | 23 | PR/IR Dept
27 |  | Gather Theme statistics/validate Theme messages | 1 day? | 2017-01-25 08:00 | 2017-01-25 17:00 | 26 | PR/IR Dept
28 |  | Interview Theme Stakeholders | 1 day? | 2017-01-26 08:00 | 2017-01-26 17:00 | 27 | PR/IR Dept
29 |  | Develop initial Theme section writeups | 1 day? | 2017-01-27 08:00 | 2017-01-27 17:00 | 28 | PR/IR Dept
30 |  | Schedule Theme Photo and Web Site Design Sessions | 1 day? | 2017-01-30 08:00 | 2017-01-30 17:00 | 29 | PR/IR Dept
31 |  | Validate Theme facts | 1 day? | 2017-01-31 08:00 | 2017-01-31 17:00 | 30 | PR/IR Dept
32 |  | Finalize Theme design and writeups with executive leadership | 1 day? | 2017-02-01 08:00 | 2017-02-01 17:00 | 31 | PR/IR Dept
33 |  | Theme production complete | 0 days | 2017-02-01 17:00 | 2017-02-01 17:00 | 32
34 |  | Develop Letter to the Shareholders | 15 days? | 2017-02-02 08:00 | 2017-02-22 17:00
35 |  | Plan interview with Chairman/CEO | 1 day? | 2017-02-02 08:00 | 2017-02-02 17:00 | 33 | PR/IR Dept
36 |  | Conduct Interview | 1 day? | 2017-02-03 08:00 | 2017-02-03 17:00 | 35 | PR/IR Dept,Chairman
37 |  | Build and review letter | 1 day? | 2017-02-06 08:00 | 2017-02-06 17:00 | 36 | PR/IR Dept
38 |  | Review letter in context with audited financial results | 1 day? | 2017-02-22 08:00 | 2017-02-22 17:00 | 37,83 | PR/IR Dept
39 |  | Letter to the Shareholders Complete | 0 days | 2017-02-22 17:00 | 2017-02-22 17:00 | 38
40 |  | Define Public and Investor Relations Focused Components | 10.5 days? | 2017-02-08 08:00 | 2017-02-22 12:00
41 |  | Set PR and IR Milestones | 0.5 days? | 2017-02-08 08:00 | 2017-02-08 12:00
42 |  | Define major PR and IR milestones (alignment with deliverables) | 0.5 days? | 2017-02-08 08:00 | 2017-02-08 12:00 | 76 | PR/IR Dept
43 |  | Develop Public Relations Messaging | 3.5 days? | 2017-02-08 13:00 | 2017-02-13 17:00
44 |  | Define PR messaging for inclusion in Annual Report | 0.5 days? | 2017-02-08 13:00 | 2017-02-08 17:00 | 42 | PR/IR Dept
45 |  | Define PR messaging about Financial Results | 2 days? | 2017-02-09 08:00 | 2017-02-10 17:00 | 44 | PR/IR Dept
46 |  | Refine distribution channels and timeline | 1 day? | 2017-02-13 08:00 | 2017-02-13 17:00 | 45 | PR/IR Dept
47 |  | Develop Investor Relations Messaging | 10 days? | 2017-02-08 13:00 | 2017-02-22 12:00
48 |  | Define IR messaging for Annual Report | 2 days? | 2017-02-08 13:00 | 2017-02-10 12:00 | 42 | PR/IR Dept
49 |  | Define IR messaging about Financial Results | 2 days? | 2017-02-10 13:00 | 2017-02-14 12:00 | 48 | PR/IR Dept
50 |  | Confirm distribution lists and channels for Annual Report reporting | 2 days? | 2017-02-14 13:00 | 2017-02-16 12:00 | 49 | PR/IR Dept
51 |  | Obtain financial results from CFO | 0.5 days? | 2017-02-22 08:00 | 2017-02-22 12:00 | 50,83 | CFO/Controller,PR/IR Dept
52 |  | Confirm mailing list acquisition and distribution process for shareholders | 4 days? | 2017-02-08 13:00 | 2017-02-14 12:00
53 |  | Confirm institutional distribution list/process | 1 day? | 2011-02-08 13:00 | 2017-02-09 12:00 | 42 | PR/IR Dept
54 |  | Confirm brokerage distribution list/process | 1 day? | 2017-02-09 13:00 | 2017-02-10 12:00 | 53 | PR/IR Dept
55 |  | Confirm individual investor distribution list/process | 1 day? | 2017-02-10 13:00 | 2017-02-13 12:00 | 54 | PR/IR Dept
56 |  | Confirm corporate Web site update/format/posting process | 1 day? | 2017-02-13 13:00 | 2017-02-14 12:00 | 55 | PR/IR Dept
57 |  | Posting & Distribution Process Confirmation Complete | 0 days | 2017-02-14 12:00 | 2017-02-14 12:00 | 56
58 |  | Public and Investor Relation Message Development & Planning Complete | 0 days | 2017-02-14 12:00 | 2017-02-14 12:00 | 57
59 |  | Perform Financial Closing Activities | 22.5 days? | 2017-01-24 08:00 | 2017-02-23 12:00
60 |  | Define Financial Review Components and Related SEC Document Scheduling | 5 days? | 2017-01-24 08:00 | 2017-01-30 17:00
61 |  | Develop Financial Close Schedule | 1 day? | 2017-01-24 08:00 | 2017-01-24 17:00 | 23 | CFO/Controller
62 |  | Develop and Confirm External Audit Review Schedule | 1 day? | 2017-01-25 08:00 | 2017-01-25 17:00 | 61 | External Auditors,CFO/Controller
63 |  | Identify/Assign resources to develop and confirm Financial Statements and notes | 1 day? | 2017-01-26 08:00 | 2017-01-26 17:00 | 62 | CFO/Controller
64 |  | Identify/Assign resources to develop and confirm 10-K Section | 1 day? | 2017-01-27 08:00 | 2017-01-27 17:00 | 63 | CFO/Controller
65 |  | Identify/Assign resources to develop and confirm Proxy Statement Section | 1 day? | 2017-01-30 08:00 | 2017-01-30 17:00 | 64 | CFO/Controller
66 |  | Financial Review and Related SEC document scheduling complete | 0 days | 2017-01-30 17:00 | 2017-01-30 17:00 | 65
67 |  | Perform Financial Close | 3 days? | 2017-01-31 08:00 | 2017-02-02 17:00
68 |  | Close out fiscal year books | 1 day? | 2017-01-31 08:00 | 2017-01-31 17:00 | 66 | CFO/Controller
69 |  | Perform review and approval of financial adjustments (Accruals and reserves) | 1 day? | 2017-02-01 08:00 | 2017-02-01 17:00 | 68 | CFO/Controller
70 |  | Develop financial results for inclusion in Annual Report, 10-K and Proxy Statement | 1 day? | 2017-02-02 08:00 | 2017-02-02 17:00 | 69 | CFO/Controller
71 |  | Financial Close and Results Complete | 0 days | 2017-02-02 17:00 | 2017-02-02 17:00 | 70
72 |  | Develop Financial Statement Notes and SEC Documents | 3 days? | 2017-02-03 08:00 | 2017-02-07 17:00
73 |  | Draft Notes to Financial Statements | 1 day? | 2017-02-03 08:00 | 2017-02-03 17:00 | 71 | CFO/Controller
74 |  | Draft 10-K | 1 day? | 2017-02-06 08:00 | 2017-02-06 17:00 | 73 | CFO/Controller
75 |  | Draft Proxy Statement information | 1 day? | 2017-02-07 08:00 | 2017-02-07 17:00 | 74 | Legal Department
76 |  | Financial Statement Notes and SEC document drafts Complete | 0 days | 2017-02-07 17:00 | 2017-02-07 17:00 | 75
77 |  | Perform External Audit | 4 days? | 2017-02-16 08:00 | 2017-02-21 17:00
78 |  | Conduct Foreign and Subsidiary Financial Audits | 1 day? | 2017-02-16 08:00 | 2017-02-16 17:00 | 91 | External Auditors
79 |  | Conduct Corporate Financial Audit | 1 day? | 2017-02-17 08:00 | 2017-02-17 17:00 | 78 | External Auditors
80 |  | External Audit Complete | 0 days | 2017-02-17 17:00 | 2017-02-17 17:00 | 79
81 |  | Review and Finalize Audit Results with Audit Committee | 1 day? | 2017-02-20 08:00 | 2017-02-20 17:00 | 80 | Audit Committee,External Auditors,CFO/Controller
82 |  | Sign off on Financial Statements/Obtain Senior Management Certifications | 1 day? | 2017-02-21 08:00 | 2017-02-21 17:00 | 81 | Audit Committee,CFO/Controller
83 |  | External Audit Complete | 0 days | 2017-02-21 17:00 | 2017-02-21 17:00 | 82
84 |  | Perform Internal Legal Review | 6 days? | 2017-02-08 08:00 | 2017-02-15 17:00
85 |  | Coordinate and review key significant events for inclusion in Annual Report | 1 day? | 2017-02-08 08:00 | 2017-02-08 17:00 | 76 | Legal Department
86 |  | Coordinate and review key significant events for inclusion in 10-K | 1 day? | 2017-02-09 08:00 | 2017-02-09 17:00 | 85 | Legal Department
87 |  | Coordinate/develop Proxy Statement development | 1 day? | 2017-02-10 08:00 | 2017-02-10 17:00 | 86 | Legal Department
88 |  | Coordinate/review Message to the Shareholders | 1 day? | 2017-02-13 08:00 | 2017-02-13 17:00 | 87 | Legal Department
89 |  | Coordinate/review External Audit review and comments | 1 day? | 2017-02-14 08:00 | 2017-02-14 17:00 | 88 | Legal Department
90 |  | Coordinate/review Senior Management certifications | 1 day? | 2017-02-15 08:00 | 2017-02-15 17:00 | 89 | Legal Department
91 |  | Internal Legal Review Complete | 0 days | 2017-02-15 17:00 | 2017-02-15 17:00 | 90
92 |  | Publicly release financial results | 0.5 days? | 2017-02-22 08:00 | 2017-02-22 12:00 | 46,83 | Audit Committee,CFO/Controller,PR/IR Dept,Chairman
93 |  | Financial Close complete | 1 day? | 2017-02-22 13:00 | 2017-02-23 12:00 | 92
94 |  | Produce Annual Report | 8 days? | 2017-02-14 13:00 | 2017-02-24 12:00
95 |  | Draft Annual Report Design Layout and Identify Placeholders | 1 day? | 2017-02-14 13:00 | 2017-02-15 12:00 | 58 | PR/IR Dept
96 |  | Prepare mockups for Executive Management | 1 day? | 2017-02-15 13:00 | 2017-02-16 12:00 | 95 | PR/IR Dept
97 |  | Iterate design/finalize production schedule | 1 day? | 2017-02-16 13:00 | 2017-02-17 12:00 | 96 | PR/IR Dept
98 |  | Finalize Annual Report Design and Placeholder data | 1 day? | 2017-02-17 13:00 | 2017-02-20 12:00 | 97 | PR/IR Dept
99 |  | Produce Final Layout/Obtain Final Approval | 1 day? | 2017-02-20 13:00 | 2017-02-21 12:00 | 98 | PR/IR Dept
100 |  | Print Annual Report | 1 day? | 2017-02-21 13:00 | 2017-02-22 12:00 | 99 | PR/IR Dept
101 |  | Obtain 10-K document file | 1 day? | 2017-02-22 13:00 | 2017-02-23 12:00 | 100 | PR/IR Dept
102 |  | Obtain Proxy Statement document file | 1 day? | 2017-02-23 13:00 | 2017-02-24 12:00 | 101 | PR/IR Dept
103 |  | Production of Annual Report Complete | 0 days | 2017-02-24 12:00 | 2017-02-24 12:00 | 102
104 |  | Distribute Annual Report | 4 days? | 2017-02-24 13:00 | 2017-02-27 12:00
105 |  | Obtain final mailing distribution lists | 1 day? | 2017-02-24 13:00 | 2017-02-27 12:00 | 103 | PR/IR Dept
106 |  | Print 10-K's for Annual Report mailings | 1 day? | 2017-02-27 13:00 | 2017-02-28 12:00 | 105 | PR/IR Dept
107 |  | Print Proxy Statements for Annual Report mailings | 1 day? | 2017-02-28 13:00 | 2017-03-01 12:00 | 106 | PR/IR Dept
108 |  | Consolidate and mail Annual Reports | 1 day? | 2017-03-01 13:00 | 2017-03-02 12:00 | 107 | PR/IR Dept
109 |  | Distribution Complete | 0 days | 2017-03-02 12:00 | 2017-03-02 12:00 | 108
110 |  | Annual Report Complete | 0 days | 2017-03-02 12:00 | 2017-03-02 12:00 | 109